## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 54 | 0 |  |  |  | 19 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 3/06 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Sat | Sun | Mon | Wed | Fri | Sat | Sun | Mon | Wed | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-02-15 | 2/17 | 2/18 | 2/19 | 2/20 | 2/22 | 2/24 | 2/25 | 2/26 | 2/27 | 3/01 | 3/03 | 3/04 | 3/05 | 3/06 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | FOREGROUND (Launchers) | [23 empty] | Assigned
6 | 1 | Launcher Prefab | CB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | Projectile Prefab (CannonBall) | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Launcher Input Handling Logic (multiple controllers!) | CB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 2 | (Basic) Launcher AI - Heuristic Based | VC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 |  | Deferred
11 | 1 | Visual Feedback for Input (Crosshairs, Arrows, ...) | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
| 1 | Physics of Cannon Movement/Projectile Firing | VC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
12 |  | BACKGROUND (Runner)
13 | 1 | Runner Prefab | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
15 | 3 | Runner Resource/Ammo Drop Prefabs | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
16 | 1 | Runner Input Handling | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
17 | 1 | Runner Health/Damage | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
18 | 1 | Runner Movement | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
19 | 1 | Background (Runner map) 1 | RZ |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
25
26
27 |  | GENERAL (Misc)
29 | 1 | Character switches control on runner death | RZ | VC | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
30 | 3 | Scorekeeping/High Score | CB | VC | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0
31 | 2 | Basic UI | CB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0
32 | 2 | Game Time Limit | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
33 | 3 | Random Player Assignment | CB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
34 | 2 | Scale foreground and background | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 19 | 19 | 17 | 16 | 15 | 14 | 12 | 10 | 9 | 8 | 7 | 5 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 54 | 54 | 48.3 | 45.5 | 42.6 | 39.8 | 34.1 | 28.4 | 25.6 | 22.7 | 19.9 | 14.2 | 8.5 | 5.7 | 2.8 | 0.0
212
213 |  | Sum | [6 empty] | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 31 | 11 | 11 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 4 | 2 | 0 | 0
217 |  |  | 3 | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 1 | 1 | 0 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Patrick Becker II | PB |  |  |  |  | PB | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 0 | 0 | 0
223 |  | Chris Boston | CB |  |  |  |  | CB | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 16 | 6 | 1 | 1 | 0 | 0
224 |  | Rita Zhao | RZ |  |  |  |  | RZ | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 5 | 5 | 0 | 0 | 0
225 |  | Valli Chockalingam | VC |  |  |  |  | VC | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 4 | 4 | 2 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
236

## Daily Scrum
Producer | 3/06 |  | Team Members
Approved | Dates |  | Patrick Becker II | Chris Boston | Rita Zhao | Valli Chockalingam | All
| 2/15 | Wed | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/16 | Thu | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/17 | Fri | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/18 | Sat | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/19 | Sun | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/20 | Mon | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Emailed professors on feasibility of getting 4 VR headsets in order to help decide project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/21 | Tue | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more. | Done: Waiting for project choice Next: Wait more.
| 2/22 | Wed | Done: Chose game idea with group. Next: Fill out burndown chart with group, assign tasks | Done: Enjoyed knowing what project we'll be doing Next: Get to it | Done: Received reply on email and met with group to decide on a project choice Next: Get started | Done: Finally agreed on a project. Next: Do it. | Done: Finally agreed on a project. Next: Do it.
| 2/23 | Thu | Done: Added basic burndown tasks Next: Get repo working | Done: Added basic burndown tasks Next: Get repo working |  | Done: Added basic burndown tasks Next: Get repo working.
| 2/24 | Fri | Done: Got github repo setup and shared with group Next: Start coding runner mechanics | Done: Went to DC. Got git working. Next: DC, can't work much |  | Done: Busy Day, Interview prep. Next: Out of town.
| 2/25 | Sat | Done: Nothing Next: Start coding runner mechanics | Done: DC Next: DC |  | Done: Traveling. Next: Out of town.
| 2/26 | Sun | Done: Nothing Next: Start coding runner mechanics | Done: DC Next: catch up/set up |  | Done: Out of town, Interview prep. Next: Out of town.
| 2/27 | Mon | Done: Figured out how the pieces of our game would fit together with group Next: Start coding runner mechanics | Done: Basic foreground, folder structure, gitignore Next: Cannons |  | Done: Busy Day, Interviews. Next: Traveling.
| 2/28 | Tue | Done: Familiazixe myself with groups code Next: Work on runner | Done: Cannon prefab/foreground platform Next: Cannon control Help: Multiple controller debugging |  | Done: Busy Day, Interviews. Next: Cannon Control functionality (post input handling)
| 3/01 | Wed | Done: Created 'runner' player and added controls Next: Meet with group to discuss what still needs to be done | Done: Cannon control basics. Pause function. Had a majority of my work overwritten when people decided it would be a good idea to do the same task as me. Added debug controller for keyboard. Next: scorekeeping | Done: Designed the most basic map ever for beginning testing, basic health reduction and powerUP utilization implemented Next: Design a less basic, more exciting map with maybe moving platforms Need: powerUP descriptions/customization, projectile customization | Done: Completed basic cannon control functionality whereby players can control pitch/yaw and firing. Added trail renderer effect for some juice in the mechanics. Next: Finish up physics and test cannon control functionality, cannon control AI. Adjust view of the game to clearly see the physics (fixed later by switching to perspective mode).
| 3/02 | Thu | Done: Scaled map background and foreground Next: Meet with group | Done: Scorekeeping details, (very) basic UI functionality. Next: Game timer | Done: Redid map design and added some water/environment Next: Player switching | Done: Busy Day, Interview. Next: Traveling back to town.
| 3/03 | Fri | Done: Met with group to discuss what we have to do next Next: Fix score incrementation and do my portion of research and analysis | Done: Game countdown timer in lower left, game pauses at end currently. Improved UI. Added random player shuffle at game start. Next: Game restart function, cannonBall despawn | Done: Color coded cannons Next: Research 1 game (at least 1.3 pages) | Done: Met with group to discuss next steps. Completed slightly buggy version of runner-cannon switching using Metadata class to notify runner of which cannon sucessfully got a shot. Next: Score Incrementing, cannon control AI, fix switching. Work on research (2 games, 2.6 pages.)
| 3/04 | Sat | Done: Nothing Next: Work on researcha nd analysis, and justification doc | Done: NY job interview. Next: odds and ends | Done: Brainstormed powerups for future game additions, tested out XBOX controller with game Next: Discuss powerups with team and confirm which ones are fun to implement | Done: Work for other classes day. Next: Get back to finishing up prototype.
| 3/05 | Sun | Done: Compiled everybodies parts of the research and analysis doc. Worked on justification doc. Next: Get feedback from instructors/classmates on our prototype | Done: Endgame message and restart functionality; playtesting. | Done: Busy, coding interview | Done: Completed switching functionality, cannon control AI and score incrementing with fixes for ensuring scoring makes sense even with the debug player (keyboard.) Next: Submission, Ensure Build is what we'd like it to be. Finish up research doc.
| 3/06 | Mon
| 3/07 | Tue
| 3/08 | Wed