## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 99 | 17 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2017-04-03 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01 | 2017-04-02 | 2017-04-03 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Get controllers working with Windows | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 |  | Assigned
6 | 2 | Submit music request by 3/22 | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | Fix start menu to work with controllers | VC | RZ | 3 | 1 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 |  | Verify?
9 | 3 | make cannon balls explode (splash damage too) | VC |  | 3 | 1 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 |  | Deferred
10 | 2 | Popup messages (X is in the lead, HIGH SCORE, etc) | CB |  | 4 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 |  | Fact of Life
11 | 2 | Reduce score accrual from time as runner | VC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  | Can't Repro
12 | 2 | Add procedurally generated powerups (shootable and grabbable) | VC |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
13 | 3 | Occasional destructable platforms | CB | PB | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
14 | 1 | Fix runner box collider | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
15 | 2 | Slow Down | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
16 | 2 | Speed Up | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
17 | 2 | Jump Higher | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
18 | 2 | Extra points | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
19 | 2 | Invincibility | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
20 | 3 | Freeze Cannons (For 2 secs) | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0
21 | 4 | Scramble Cannons | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
22 | 1 | Runner Variable Jump | PB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
23 | 4 | Switch cannon and runner powerups | RZ |  | 1 | 1 |  |  | 1 | bar: 2017-03-20 to 2017-04-03
25 | 1 | Fix the runner (movement parent) | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
26 | 1 | Add light trail to cat | VC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
27 | 3 | Add characters to cannons | RZ |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
28 | 3 | Change background to metallicy techno stuff | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
29 | 2 | Color Code Trail | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
30 | 4 | Red/Green/Yellow/Blue Characters | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
31 | 3 | Character selection and color mapping | RZ |  | 5 | 3 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3
35 | 2 | Powerup Audio | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
36 | 1 | Fix up Pause Menu (restart/quit) | CB |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0
37 | 3 | New backgrounds & textures | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
38 | 4 | controller inversion checkbox |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
39 | 2 | Platform generation balancing | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
40 | 1 | Making UI Larger, UI Scaling Issues | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
41 | 1 | Runner movement |  |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
42 | 1 | Denoting Cannon Hit Location | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
43 | 3 | Break platform sound | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
44 | 1 | Stop cannon fire during switch (solves the problems of continual switching) | VC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
45 | 2 | Fix runner not being able to jump off platforms bug | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
46 | 3 | Test gameplay with vertical moving platforms | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
47 | 3 | Delete platforms when reach end of path | PB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
48 | 2 | Runner speed/jump power balancing | PB |  | 2 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
49 | 4 | Prototype climbing style platformer | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 99 | 99 | 91.9286 | 84.8571 | 77.7857 | 70.7143 | 63.6429 | 56.5714 | 49.5 | 42.4286 | 35.3571 | 28.2857 | 21.2143 | 14.1429 | 7.0714 | 0
212
213 |  | Sum | [6 empty] | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 31 | 15 | 4 | 4
216 |  |  | 2 | [5 empty] | 29 | 29 | 29 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 25 | 14.5 | 6 | 6
217 |  |  | 3 | [5 empty] | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 23 | 14.5 | 4 | 4
218 |  |  | 4 | [5 empty] | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 4 | 3 | 3
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Rita Zhao | RZ |  |  |  |  | RZ | 24 | 24 | 24 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 17 | 4 | 4
223 |  | Chris Boston | CB |  |  |  |  | CB | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 4 | 2 | 2
224 |  | Valli Chockalingam | VC |  |  |  |  | VC | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 16 | 5 | 5
225 |  | Patrick Becker II | PB |  |  |  |  | PB | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 16 | 12 | 6 | 1 | 1
226 |  | All | ALL |  |  |  |  | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99 | 99
236

## Daily Scrum
Producer | 2017-04-03 |  | Team Members
Approved | Dates |  | Rita Zhao | Chris Boston | Valli Chockalingam | Patrick Becker II | All
| 2017-03-20 | Mon | Done: 485 Next: 485 | Done: Trying not to fail 484 Next: Same | Done: Next: Catch up, figure out what to do Help: Need to talk with everyone | Done: Work for other classes Next: Same
| 2017-03-21 | Tue | Done: 485 Next: 485 | Done: Trying not to fail 484 Next: Same | Done: Caught up. Set up GIT Next: Prototype enemies Help: — | Done: Work for other classes Next: Same
| 2017-03-22 | Wed | Done: 485, Submitted music request... Next: 485 | Done: Trying not to fail 484 Next: Same |  | Done: Work for other classes Next: Playtest implementation
| 2017-03-23 | Thu | Done: 485 Next: 485 | Done: Trying not to fail 484 Next: Same |  | Done: Found friends who would be willing to playtest the other groups game. Set up a time for playtest Next: Meet with friends to have them perform playtest
| 2017-03-24 | Fri | Done: 485 Next: 485 | Done: Trying not to fail 484 Next: Same |  | Done: Met with group for playtesting Next: Compile notes on playtest
| 2017-03-25 | Sat | Done: 485 Next: 485 | Done: Trying not to fail 484 Next: Same |  | Done: Wrote executive summary and compiled notes from all of our groups playtests Next: Start on burndown items
| 2017-03-26 | Sun | Done: 485 Next: 485 | Done: Trying not to fail 484 Next: Same |  | Done: Work for other classes Next: Same
| 2017-03-27 | Mon | Done: 485 Next: 388 | Done: Trying not to fail 484 Next: Same |  | Done: Work for other classes Next: Same
| 2017-03-28 | Tue | Done: 388 Next: 388 | Done: Trying not to fail 484 Next: Same |  | Done: Work for other classes Next: Same
| 2017-03-29 | Wed | Done: 388 Next: 494 | Done: Trying not to fail 484 Next: Same |  | Done: Work for other classes Next: Prototype new level ideas
| 2017-03-30 | Thu | Done: Sketched prefabs for powerup objects Next: Line and color | Done: Finished 484 Project Next: Power through burndown items |  | Done: Played around with a 'climbing' style platformer. Did not work well with our game Next: Experiment with implementation of vertical platforms
| 2017-03-31 | Fri | Done: Finished prefabs images for powerups, started sketching characters Next: Decide on how the characters should look with cannons | Done: Prefab for destructable platforms, new backgrounds and textures Next: Integrate destructable platforms |  | Done: Fixed runner box collider and fixed jump bugs Next: Experiemtn with implementatin of vertically moving platforms
| 2017-04-01 | Sat | Done: Decided on small ppl and finished making them Next: Move everything to unity and start programming for color switching clarity | Done: Destructable platform spawning, destructable platform sound effects, dynamic background generation, powerup audio, new and improved pause menu, fixed UI scaling issues Next: popups |  | Done: Played around with vertically moving platforms, does not work well with our game. Did some balacing on platform generation. Next: Polish playtest preparation, and getting our project ready for submission.
| 2017-04-02 | Sun | Done: color switching, new runner animation | Done: Framework for popup messages, added some to powerup pickup. Next: Color code popups, add some for high score/ Help: associating player ids with popup messages |  | Done: Polished playtest implementation, justification doc, minor bug fixes Next: Turn in project and wait for feedback
| 2017-04-03 | Mon
| 2017-04-04 | Tue
| 2017-04-05 | Wed
| 2017-04-06 | Thu
| 2017-04-07 | Fri
| 2017-04-08 | Sat
| 2017-04-09 | Sun
| 2017-04-10 | Mon