## Main
cont | Today | Copy this doc and follow the link below for instructions. |  |  | 76 | 10 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2017-04-21 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
NOTE: Tasks should focus on refining features, not adding new ones
8 | 1 | Fix all menus to work with controllers | RZ | VC | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Fixed
9 | 1 | Add procedurally generated powerups (shootable and grabbable) | VC |  | 4 | 0 |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Improve Variable Jump | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 |  | Fact of Life
11 | 3 | (Slight) Splash damage from exploding cannonballs | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 2 | Popup messages (X is in the lead, HIGH SCORE, etc) | CB | VC | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
13 | 4 | Switch cannon and runner powerups (Cannon Powerups?) |  |  | 1 | 1 |  |  | 1 | bar: 2017-04-03 to 2017-04-17
14 | 4 | randomize players to cannon/runner | RZ |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0
14 | 2 | Runner speed/jump balancing | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
18 | 1 | Fix character swap color glitch (debug w/ controllers) | VC |  | 2 | 0 |  |  | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | Fix score color glitch (debug w/ controllers) | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0
20 | 3 | Background missing hex? | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
21 | 2 | Add floor to map | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 3 | Debug runner animations (directions) | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
23 | 3 | chara animation while controlling cannons | RZ |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
24 | 3 | Pause Cannon AI when Paused Menu is shown | VC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1 | Faster Cannon Movement | VC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
27 | 1 | Powerup System functional fixes (timers for all powerups except points, disallow doubling effects, handle clobbering effects, remove effects on swap, freeze cannon functionality.) | VC |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
28 | 1 | Promo image | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | Trailer | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Runner trail fix upon falling | VC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
31 | 1 | Player Movement out of Bounds | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0
8 | 1 | Re-design bottom platform | PB |  | 2 | 0 |  |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | Fixed
33 | 1 | Fix trailer based on instructor feedback | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
34 | 2 | Balance platform spawn rate | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1 | runner movement is weird/platforming fix |  |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
36 | 1 | cat moonwalk fix |  |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
37 | 1 | Tutorial scene |  |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
38 | 1 | making the game a complete game w stages | RZ |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
39 |  | Menu scaling | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 76 | 76 | 70.5714 | 65.1429 | 59.7143 | 54.2857 | 48.8571 | 43.4286 | 38 | 32.5714 | 27.1429 | 21.7143 | 16.2857 | 10.8571 | 5.4286 | 0
212
213 |  | Sum | [6 empty] | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5 | 75.5
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 46 | 45.5 | 39 | 39 | 39 | 38.5 | 34.5 | 34.5 | 31.5 | 31.5 | 25.5 | 25.5 | 21.5 | 19.5 | 12 | 9
216 |  |  | 2 | [5 empty] | 13 | 13 | 13 | 13 | 10 | 10 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 0 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 10 | 7 | 6 | 4 | 2 | 2 | 2 | 0 | 0
218 |  |  | 4 | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 1 | 1
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Patrick Becker | PB |  |  |  |  | PB | 12 | 12 | 11 | 11 | 10 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 0 | 0
223 |  | Chris Boston | CB |  |  |  |  | CB | 13 | 13 | 13 | 13 | 11 | 11 | 6.5 | 6.5 | 4.5 | 3.5 | 3 | 3 | 3 | 3 | 0 | 0
224 |  | Rita Zhao | RZ |  |  |  |  | RZ | 13 | 13 | 13 | 13 | 13 | 12.5 | 12.5 | 11.5 | 10.5 | 8.5 | 8.5 | 6.5 | 6.5 | 5.5 | 3 | 0
225 |  | Valli C | VC |  |  |  |  | VC | 25 | 24.5 | 19 | 19 | 19 | 19 | 13 | 13 | 12 | 12 | 8 | 8 | 4 | 2 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76
236

## Daily Scrum
Producer | 2017-04-21 |  | Team Members
Approved | Dates |  | Patrick Becker | Chris Boston | Rita Zhao | Valli C | All
| 2017-04-03 | Mon | Done: Discussed level design with the group Next: Implement some of the level design that we decided in | Done: Talked about level design Next: Don't fail 484 |  | Done: Prototyped movement Next: Text movement with friends Help: Need to meet with friends
| 2017-04-04 | Tue | Done: Work for other classes. Next: Work on level design. | Done: Trying not to fail 484 Next: Don't fail 484 |  | Done: Tested movement; it didn't go very well :( Next: Redesign movement and prototype Help: I'd like to talk with Ryan about movement design.
| 2017-04-05 | Wed | Done: Took out floor gaps. Next: Work on balancing jump power and player speed | Done: Trying not to fail 484 Next: address map floor issue
| 2017-04-06 | Thu | Done: Balanced jump power based on platform heights Next: Modify runner speed | Done: Add floor to map, add appropriate textures, test with runner AI and powerups Next: Popup research
| 2017-04-07 | Fri | Done: Balanded runner speed Next: Modify platform spawn rate | Done: found several good tutorials on how to create text popups for scoring Next: Implement them | Done: start up menu + controllers
| 2017-04-08 | Sat | Done: Work for other classes. Next: Modify platform spawn rate | Done: Created framework for text popups, with support for size and custom text, along with audio Next: Look into background hex problem
| 2017-04-09 | Sun | Done: Game trailer Next: Modify platoform spawn rate | Done: Took car into shop, couldn't end up doing much else Next: Look into background hex problem | Done: fixed up sprites with colors that pop better and don't blend
| 2017-04-10 | Mon | Done: Work for other classes. Next: Modify platform spawn rate | Done: Fixed issue where center background hex wouldn't appear Next: Adddress menu scaling problem | Done: promo image in class, much success, much rainbow
| 2017-04-11 | Tue | Done: Increased spawn rate of lower platforms, decreased it for higher platforms Next: Testing and debugging | Done: Fixed menu scaling issue, tested to make sure I didn't break anything Next: Popup tweaks? | Done: started chara selection menu, added new sprites and modified existing code so that things would be based on color, also got together with team and created material for the promotional video
| 2017-04-12 | Wed | Done: Testing and debugging Next: Modify game trailer based on feedback | Done: Popups completed and working in all cases Next: 481 Project
| 2017-04-13 | Thu | Done: Work for other classes Next: Modify game trailer based on feedback | Done: 481 Project Next: 481 Project | Done: runner animation slowed down, i find the switch back and forth very endearing
| 2017-04-14 | Fri | Done: Improvements on variable jump Next: Modify game trailer | Done: 481 Project Next: 481 Project
| 2017-04-15 | Sat | Done: Modified game trailer Next: Testing and debugging | Done: 481 Project Next: Minor tweaks as brought up in meeting | Done: more chara selection, modified the size of the prefabs for powerups
| 2017-04-16 | Sun | Done: Testing and debugging Next: Testing and debugging | Done: Small tweaks to background generation and menu scale Next: Music | Done: pause menu + controllers, chara selection too hard, just put to randomize, finished fine tuning the animation of the cannon sprites, also removed the mouse pointer, reduced the game time by 30 sec, added a panel to the end game message
| 2017-04-17 | Mon | Done: Testing and debugging. | Done: playtesting
| 2017-04-18 | Tue
| 2017-04-19 | Wed
| 2017-04-20 | Thu
| 2017-04-21 | Fri
| 2017-04-22 | Sat
| 2017-04-23 | Sun
| 2017-04-24 | Mon