## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 87 | 26.5 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 3/19 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-03-06 | 3/07 | 3/08 | 3/09 | 3/10 | 3/11 | 3/12 | 3/13 | 3/14 | 3/15 | 3/16 | 3/17 | 3/18 | 3/19 | 3/20 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
8 | 1 | Fix/test scoring | VC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Make game work with 4 xbox controllers | VC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 2 | Runner AI | PB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
11 | 2 | Improve cannon AI | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
12 | 2 | Cannonball (predictive) trajectory line | VC |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3 | Cannonball color match player | VC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Power up Prefabs | RZ |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 2 | Moving Platforms / Procedural Generation | PB | RZ | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 1 | 0 | 0
17 | 2 | Runner can pickup powerups | PB | RZ | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
18 | 4 | Cannon Charge Power (adjustable velocity) | ALL |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
19 | 3 | Background Music in Game | CB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 4 | Runner Sprite/Animation | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1 | Start Menu | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 4 | Pick sprites | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Tell how many people are playing (press A) | RZ |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 4 | Character design <3 | RZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3 | Background Music in Menu | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
27 | 4 | Destroy cannonballs on player switch | PB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 4 | When runner falls off map, swap with longest cannon | CB | VC | 3 | 1 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1
29 | 1 | Animation for switch, Inspiration: See around 0:40 in https://www.youtube.com/watch?v=Dzx1ZIIiwtE (Peggle Fever) | VC |  | 3 | 1.5 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
30 | 1 | Invincibility Time Period for new runner post switch | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
31 | 1 | Scoring for AIs | VC |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
32 | 1 | Make clear Controller - Player Mapping (Score Text - Cannon/Runner Color matching) | VC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
33 | 1 | Controller Remapping (Intuitiveness) | VC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
34 | 4 | Larger more clear UI for scores | CB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
35 | 2 | Cannon AI improvements | PB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
36 | 3 | Pretty things (people on the cannons for now, and a better animation for runner) | RZ |  | 10 | 10 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
37 | 3 | instructional page | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
38 | 1 | Make gameplay less distracting (1. Reduce rate of firing, 2. Make runner faster/more responsive, 3. Changing conditions for cannonball destruction...) | VC |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
39 | 1 | make controllers work on windows | CB |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
40 | 1 | Controller + startup menu | RZ |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
41 | 3 | Resize cannons/world to give runner more room | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
42 | 2 | Create new map(box) with moving platforms | PB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 87 | 87 | 80.8 | 74.6 | 68.4 | 62.1 | 55.9 | 49.7 | 43.5 | 37.3 | 31.1 | 24.9 | 18.6 | 12.4 | 6.2 | 0.0
212
213 |  | Sum | [6 empty] | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 0
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 28 | 28 | 28 | 28 | 28 | 27 | 24 | 22 | 20 | 20 | 20 | 11.5 | 9.5 | 6.5 | 6.5 | 6.5
216 |  |  | 2 | [5 empty] | 23 | 23 | 23 | 23 | 23 | 23 | 16 | 14 | 14 | 14 | 14 | 12 | 12 | 9 | 6 | 6
217 |  |  | 3 | [5 empty] | 22 | 22 | 22 | 22 | 22 | 21 | 17 | 17 | 17 | 17 | 17 | 15 | 13 | 10 | 10 | 10
218 |  |  | 4 | [5 empty] | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Patrick Becker II | PB |  |  |  |  | PB | 19 | 19 | 19 | 19 | 19 | 19 | 15 | 13 | 13 | 13 | 13 | 9 | 9 | 6 | 3 | 3
223 |  | Chris Boston | CB |  |  |  |  | CB | 19 | 19 | 19 | 19 | 19 | 19 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 1 | 1 | 1
224 |  | Rita Zhao | RZ |  |  |  |  | RZ | 23 | 23 | 23 | 23 | 23 | 22 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
225 |  | Valli Chockalingam | VC |  |  |  |  | VC | 23 | 23 | 23 | 23 | 23 | 22 | 17 | 15 | 13 | 13 | 13 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
226 |  | All | ALL |  |  |  |  | ALL | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 0
236

## Daily Scrum
Producer | 3/19 |  | Team Members
Approved | Dates |  | Patrick Becker II | Chris Boston | Rita Zhao | Valli Chockalingam | All
| 3/06 | Mon | Done: Presented prototype to class. Next: Meet with group to discuss feedback. | Done: Planned X Next: Implement X Help: — | Done: Presentation of prototype successful Next: Meet on Wednesday to discuss what to finish for next sprint | Done: Presented Prototype in class, Got feedback on next steps. Xbox controllers borrowed. Next: Meet to decide on new burndown chart tasks and fix priorities.
| 3/07 | Tue | Done: Nothing today. Next: Meet with group to discuss feedback from prototype presentation. |  | Done: Project for another class Next: Need to meet with group | Done: Thought about feedback and next steps. Otherwise busy. Next: Meet tomorrow.
| 3/08 | Wed | Done: Met with group. Completed burndown chart and decided who would complete each task. Next: Work on tasks assigned to me on the burndown chart. |  | Done: Met, filled out burndown chart Next: Start on the burndown | Done: Met group to finish up burndown chart tasks. Next: Start working on tasks, primarily from fixes (controllers, AI, scoring...)
| 3/09 | Thu | Done: Nothing today. Next: Work on tasks assigned to me on the burndown chart. |  | Done: Nothing related to this class Next: Do something | Done: Busy. Next: Start working on predictive line for cannons and match cannonball colors to the cannon colors (simple and relatively quick tasks).
| 3/10 | Fri | Done: Familiarized myself with current cannon AI. Made tweaks to improve. Next: Finish cannon AI and work on runner AI. |  | Done: Started a bit of the start menu Next: Finish the start menu | Done: Completed cannonball color matching and predictive line for cannons, started work on multiple Xbox controller support and some simple steps towards runner position based cannon AI control. Next: Complete Controller support,
| 3/11 | Sat | Done: Finished runner AI. Not perfect but good for now. Next: Cannon AI and runner tasks. |  | Done: Start menu done Next: Character selection and character animation Help: Start menu does not work with xbox controllers when trying to select "play" with any of the buttons, but can move between choices | Done: More work on controller support, began refactoring and cleaning up some of the Input code to reduce code duplication. Next: Finish up controller support.
| 3/12 | Sun | Done: Finished cannon AI. Not perfect but better than before. Next: Turn in Gold Spike. |  | Done: Very rudimentary animation for the character. Somehow the image won't render as soon as material was attached so it looks very weird... Bare bones of character selection menu started, not finished yet. The character choices have been sketched. Next: Fix that animation and flesh out the characters so that they can be used along with the cannons and the selection menu. Make the selection menu work with multiple players. Help: I read that Unity has a problem with seeing multiple controllers as 1 input, will have to ask about this and get an adapter for the controller because the one received in class does not have a USB connection. | Done: Completed controller support (for Macs) with additions so that runner control and cannon firing starting and stoppping is functional. Next: New branch was created, need to merge (merge conflicts showed up.)
| 3/13 | Mon | Done: Had students in class test goldspike. Next: Discuss upcoming design sprint with group. |  |  | Done: Completed merge of master into new branch and then new branch into master. Controllers seem to work with all the other character sprites and AI work (again, only tested on Mac.) Next: Fix up any assertions or mission component errors that arise and work on other remaining tasks in burndown chart (may need to add some tasks or create a new chart.) Another note: Scoring marked as complete as it is functional but not quite intuitive (scores work appropriately for all human players, AI scores don't get calculated yet though.)
| 3/14 | Tue | Done: Nothing. Next: Discuss upcoming design sprint with group.
| 3/15 | Wed | Done: Met with group to update burndown chart, discuss feedback from the testing in class, and decide who will do what in the upcoming week.
| 3/16 | Thu | Done: Worked on procedural generation for moving platforms. Next: Finish procedural platform generation. |  | Done: Moving platforms
| 3/17 | Fri | Done: Finished with moving platforms that are randomly generated. Next: Make a new map that incorporates moving platforms.
| 3/18 | Sat | Done: Finished new map with moving platforms. Next: Balance platform spawn speed and movement speed for more engaging gameplay.
| 3/19 | Sun | Done: Cannon AI improvements, cannon and map scaling for easier runner visibility. Next: Prepare project for alpha.
| 3/20 | Mon
| 3/21 | Tue
| 3/22 | Wed
| 3/23 | Thu
| 3/24 | Fri
| 3/25 | Sat
| 3/26 | Sun
| 3/27 | Mon